## ADKAR
Stakeholder | Awareness - of the need for change | Desire - to participate in change | Knowledge - how to change | Ability - to implement change | Reinforcement - to sustain the change
Customer | Unknown: may not know a portal exists or why it might help them | Low: currently familiar with calling agents but may prefer web portals for convenience - there is an assumption that delayed / missed manual follow-ups are preventing debt collections but no hard evidence | Low: Have no direct training on using the portal, although many users may be familiar with online payment / banking systems | Unknown: varying levels of digital ability assumed but no evidence | Low: A Legacy-Trust-led change will offer the opportunity for all customers to use a web portal, but there is no enforcement
Agent | Medium-high: aware of the time and stress to consolidate records in order to serve customers, lots of time spent on low-complexity cases | Medium: likely frustrated by time pressure and work stress, but little direct evidence to support this | Medium-high: full training will be provided, and experience over time will provide confidence, but exception-case handling may take time to understand well | Medium-high: full training will be provided, workflow has been mapped, but agent skill with portal will take time to develop | Low (high-risk): agents may find workarounds as is the current practice
Manager | High: project stakeholders, with clear evidence of awareness of operational pain points | High: With clear process map and justified recommendations, in favour of operational efficiencies - though with concerns about creating more work or ambiguity | Medium-high: training will be provided; there is a time-cost to developing familiarity with the portal; managing agents and the new workflows may take some time to develop confidence in | Medium: assumed competency in management and familiarity with team, but no direct evidence on ability to navigate the change well | Medium: KPI alignment will motivate change management, but these are assumed and not evidenced
Executive | High: Danile Okoye is aware of revenue leakage and likely operation inefficiencies too | High: with justified economic and operational case (ROI), in favour of recovering lost leakage and improving workflows | Low: likely little awareness of operational pain points or experience of practical causes of revenue leakage; has a more strategic, high-level view of the business | High: budget-holder and policy-setting authority, will approve (or gain approval from board) on any strategic change | Medium: revenue recovery will motivate and validate value of change, but no formal process (apparently) to reinforce it

## Risks
Risks | Mitigations | Flags
Agent bypass: agents will develop workarounds if the portal creates more work or fails to handle exceptions well (as is the current practice); named as a high risk by Gareth | Workflow mapping; full training and concise agent-user documentation to be provided | Backlog items: agent user-acceptance testing (UAT); agent training; reporting requirement: weekly feedback on portal quality, usage and workarounds to track workarounds
Customer drop-off: customers attempt portal, have a bad experience, bypass portal and return to old methods - consider that customers have no documented digital ability, awareness of need for change, desire for change | Testing with users; clear error message; clear "Speak-to-Agent" (S2A) option; feedback opportunities | Backlog item: UX testing; reporting requirement: portal abandonment rate and S2A selection rate
Inconsistent reinforcement: across all stakeholder groups, there is no clear process to enforce portal use or adoption; risk of falling into old habits | Adoption KPIs for agents, managers, executives | Reporting requirement: portal adoption / use rate (perhaps a measure of cases attempted and solved)
Executive disengagement: over time, portal value goes unassessed and lose clarity on portal operational benefits | Monthly reporting of adoption statistics, case handling success and agent/manager feedback sent to executives | Reporting requirement: portal adoption / use rate (perhaps a measure of cases attempted and solved); executive briefing message: regular reporting to validate portal and identify improvements
Agent knowledge gaps: at portal handover (S2A) or data retrieval | Define and document clear escalation protocols in guide for agents and managers; manager- and agent-user documentation for DB hybrid history dashboard | Backlog items: documentation for escalation protocols and (agent-facing) customer history dashboard; agent training